## Sheet1
ID | Predecessors | Task Owner | Start Date | End Date | Description | Additional members
SE_N15_PLAN_01 | PLAN_02 - 05 | Sam Sherar | 2012-10-09 | 2012-11-01 | Writing the Overall Document
SE_N15_PLAN_02 |  | Cellen Williams | 2012-10-09 | 2012-11-01 | Creating Use Case diagrams
SE_N15_PLAN_03 |  | Andy Watkins | 2012-10-09 | 2012-11-01 | User Interaction design
SE_N15_PLAN_04 |  | Charlie Bird | 2012-10-09 | 2012-11-01 | Risk Analysis
SE_N15_PLAN_05 |  | Sam Sherar | 2012-10-09 | 2012-11-01 | Gantt Chart
SE_N15_TEST_01 |  | Grant David | 2012-10-28 | 2012-11-10 | Writing the Test Document
SE_N15_TEST_02 | TEST_01 | Grant David | 2012-12-01 | 2013-01-08 | Testing Prototypes | Imran Mungul
SE_N15_TEST_03 | TEST_02 | Grant David | 2012-01-29 | 2013-02-04 | Testing Final Product | Imran Mungul
SE_N15_DS_01 | DS_02 - 05 | Charlie Bird | 2012-11-02 | 2012-12-11 | Writing the Overall Document
SE_N15_DS_02 |  | Imran Mungul | 2012-11-02 | 2012-11-16 | Decomposition Description
SE_N15_DS_03 |  | Andy Watkins | 2012-11-02 | 2012-11-16 | Dependancy Description
SE_N15_DS_04 |  | Cellen Williams | 2012-11-02 | 2012-11-16 | Interface Description
SE_N15_DS_05 |  | Fiona Samy | 2012-11-02 | 2012-11-16 | Detailed Design
SE_N15_DS_06 |  | Kamil Mrowiec | 2012-11-01 | 2012-11-08 | Researching DBMS Systems (Prosgres vs MySql)
SE_N15_CODE_01 | CODE_02 - 04 | Kamil Mrowiec | 2012-11-02 | 2012-12-01 | Prototypes
SE_N15_CODE_02 |  | Kamil Mrowiec | 2012-11-02 | 2012-12-01 | Server-Server Interaction
SE_N15_CODE_03 |  | Andy Watkins | 2012-11-17 | 2012-12-01 | User Interface
SE_N15_CODE_04 |  | Sam Sherar | 2012-11-02 | 2012-12-01 | Data Persistance and Modelling
SE_N15_CODE_05 | CODE_01 | Kamil Mrowiec | 2012-12-01 | 2013-02-05 | Developing Final Product | Sam Sherar, Andy Watkins, Cellen Williams
SE_N15_MAN_01 |  | Fiona Samy | 2013-01-29 | 2013-02-10 | Writing User Manual
SE_N15_MAN_02 |  | Imran Mungul | 2013-01-29 | 2013-02-10 | Writing Technical Manual
SE_N15_FR_01 |  | Sam Sherar | 2012-02-06 | 2012-02-16 | Writing Final Report | Everyone
SE_N15_FR_02 | PLAN | Andy Watkins | 2012-02-06 | 2012-02-16 | Finalising Project Plan document
SE_N15_FR_03 | TEST | Grant David | 2012-02-06 | 2012-02-16 | Finalising Test Document
SE_N15_FR_04 | MAN | Fiona Samy | 2012-02-10 | 2012-02-16 | Finalising User manual
SE_N15_FR_05 | DS | Imran Mungul | 2012-02-10 | 2012-02-16 | Finalising Design Specification document